## Reg 17 REview
Status Key
[7 empty] | Completed |  | C
[7 empty] | In Progress |  | I
[7 empty] | Not Commenced |  | N
Risk Management Task Listing
Ref | Finding | Recommendation | Task/s | Source | Timeline | Responsibility | Details of Actions | Status
1. RISK MANAGEMENT
1.1 |  | The Risk Management Framework should be adopted by Council on an ongoing basis. | Present the Shire’s Risk Management Framework to the Audit Committee & Council annually for review. | Regulation 17 Review 2014 | December annually | Principal Environmental Health Officer | Last done Dec 2017 | Completed | c
1.2 |  | Develop, adopt and implement a Business Continuity Plan, incorporating a Disaster Recovery Plan. | Prepare a draft Business Continuity Plan which incorporates a Disaster Recovery Plan and procedures. | Regulation 17 Review 2014 | 2016-12-01 | Manager Development & Environmental Services | LGIS to be engaged to commence work on BCP in April/May 2016. Was deferred, timeline to be reviewed. | Not Commenced | N
1.2.1 |  | Include the following as a minimum in the Plan: | Present the draft BCP to Council for adoption. | Regulation 17 Review 2014 | 2017-10-01 | Chief Executive Officer | LGIS have provided a cost estimate to work with Council staff to prepare a Business Continuity Plan. Staff are currently investigating options to fund this program. IT Business Continuity will be addressed as part of this process. | Not Commenced | N
1.2.2 |  | An impact analysis establishing various scenarios and their efficient resolution including logistical as well as IT related issues |  | Regulation 17 Review 2014 |  | Chief Executive Officer |  | Not Commenced | N
1.2.3 |  | Consideration and evaluation of temporary alternative sites from which significant operating functions can be conducted in the event of unforseen events |  | Regulation 17 Review 2014 |  | Chief Executive Officer |  | Not Commenced | N
1.2.4 |  | Ensuring critical business functions can be completed whilst IT systems are unavailable |  | Regulation 17 Review 2014 |  | Chief Executive Officer |  | Not Commenced | N
1.2.5 |  | The Plan should be developed in consultation with relevant staff and third party suppliers, communicated to all staff, implemented and monitored on a regular basis. | Communicate BCP to all staff once adopted. | Regulation 17 Review 2014 | 2016-07-01 | Manager Development & Environmental Services | Timeline dependent upon receipt of LGIS report. | Not Commenced | N
1.2.6 |  | Develop procedures to identify when changes are required to the plan as a result of IT infrastructure changes. | Test the BCP, record results, and update/review annually, including communicating to all staff. | Regulation 17 Review 2014 | October annually (after adoption) | Manager Development & Environmental Services | As above | Not Commenced | N
1.2.7 |  | Test the plan annually and the results from the test to be documented along with corrective action taken to eliminate weaknesses. |  | Regulation 17 Review 2014 |  | Manager Development & Environmental Services |  | Not Commenced | N
1.3 |  | We recommend the Local Emergency Recovery Plan be reviewed and adopted by Council. Once the plan and encompassing documents have been adopted, we recommend it is endorsed and communicated to all staff, implemented and monitored on a regular basis including testing the appropriate sections of the plan to ensure that in the event of a disaster, appropriate actions can be taken. | The Local Emergency Recovery Plan documents are being reviewed with an exercise undertaken annually. | Regulation 17 Review 2017 | 2017-10-01 | Manager Development & Environmental Services | The Local Emergency Recovery Plan and the Local Emergency Management Arrangements were reviewed and adopted by Council in 2016 & 2017 retrospectively. They are both located on the Shire website.Both plans are exercised as determined through the Local Emergency Management Committee. | Completed | C
1.4 |  | We recommend the Long Term Financial Plan and Asset Management Plan be finalised and adopted by Council. Once the plans have been adopted, we recommend they are endorsed and communicated to all staff, implemented and monitored on a regular basis. | Complete the finalisation of the Long Term Financial Plan and the Asset Management Plan | Regulation 17 Review 2017 | In Progress | Manager Finance & Administration Manager Development & Environmental Services | An updated Long Term Financial Plan was adopted by Council on 8th August 2017. | In Progress | i
1.4.1 |  |  | The completed plans shall be endorsed by council and monitored on a regular basis | Regulation 17 Review 2017 |  | Manager Finance & Administration Manager Development & Environmental Services | Asset Management Plans have been developed as at 30/6/2016 and are currently being brought up-to-date prior to presentation to Council for adoption. | In Progress | i
1.4.2 |  |  | The endorsed plans shall be communicated to all staff | Regulation 17 Review 2017 |  | Manager Finance & Administration Manager Development & Environmental Services |  | In Progress | i
1.5 |  | The Shire of Donnybrook-Balingup design and implement a conflict of interest register. This register should be monitored to ensure that all conflicts (whether perceived/actual) are disclosed. All conflicts of interest should be managed accordingly by the Shire. | A conflict of interest register shall be developed and monitored | Regulation 17 Review 2017 | 2017-07-01 | Governance officer | Register kept in the Executive area. Signed off by CEO. | Completed | C
1.6 |  | We recommend a formal procedure is implemented to monitor lessee compliance with terms of Council leased properties which could include updating the lease register to include insurance details and any other lessee reporting requirements. | A letter shall be designed and sent annually to lessees | Regulation 17 Review 2017 | Ongoing | Governance Officer |  | In Progress | i
1.7 |  | As best practice, and as outlined within operational guideline 09 we suggest the Shire’s Risk Management Framework include a: | To pursue the development of suggested Policies | Regulation 17 Review 2017 |  | Governance Officer | Policy review has been postponed from April 2017 to later in the year. | Not Commenced | N
1.7.1 |  | Litigation/Claims Policy; |  | Regulation 17 Review 2017 | 2017-06-01 | Governance Officer | Policy review has been postponed from April 2017 to later in the year. | Not Commenced | N
1.7.2 |  | Fraud Control Policy |  | Regulation 17 Review 2017 | 2017-06-01 | Governance Officer | Policy review has been postponed from April 2017 to later in the year. | Not Commenced | N
1.7.3 |  | Environment Management Policy. |  | Regulation 17 Review 2017 | No time frame | Governance Officer | Policy review has been postponed from April 2017 to later in the year. | Not Commenced | N
1.8 |  | Designs and implements a central contractor/sub-contractor insurance register which is maintained by one individual to ensure that all contractor insurances are up to date. | Shire will look at developing internal procedure/system. | Regulation 17 Review 2017 | 2017-12-01 | OHS Officer | Currently not included in the OSH Co-ordinator’s KPI’s for the next 12 months. | Not Commenced | N
1.9 |  | We recommend Council investigate obtaining cybercrime insurance. | The Shire shall obtain a quote to include Cybercrime insurance at the time of the next renewal. | Regulation 17 Review 2017 | 2017-11-01 | Manager Finance & Administration | Cybercrime Insurance Liability insurance was effected from 1/7/2017 | Completed | C
1.1 |  | The Public Interest Disclosure procedure should be reviewed and updated on a regular basis. | Update and review the PID procedure. | Regulation 17 Review 2017 | 2016-06-01 | Governance Officer | reviewed annually, last reviewed June 2017 | Completed | C
2. INTERNAL CONTROLS
2.1 |  | Finalise and adopt the draft Project Management Plan template. | Finalise the Project Management Plan template for use with major projects and present to Council for adoption. | Regulation 17 Review 2014 | 2016-06-01 | Chief Executive Officer |  | Not Commenced | N
2.2 |  | Undertake formal performance management assessments as per the WALGA guidelines at the completion of tender periods once goods/services have been tendered, and utilise compliance checklists in managing project contracts. | Update the Project Completion Report template in the Project Management Plan template (as per above task) to reflect WALGA guidelines. | Regulation 17 Review 2014 | 2016-06-01 | Executive Assistant |  | Not Commenced | N
2.3 |  | Include KPI’s/ performance criteria, monitoring and performance assessment procedures, and action as a result of underperformance, within formal legal contracts. | Consider setting KPI’s/ performance criteria, monitoring and performance assessment procedures, and action as a result of underperformance, within formal legal contracts for major Shire projects. | Regulation 17 Review 2014 | 2016-06-01 | Executive Management Team | EMT to review | Not Commenced | N
2.4 |  | Develop and implement an ongoing security awareness program to ensure security needs of the Shire are updated as required (for example due to IT infrastructure or application changes) and to prevent any security breaches from occurring. This could be incorporated as part of the Shire’s overall Risk Management Framework. | Develop a procedure detailing the process for communicating changes to staff when security measures are updated, including for IT hardware/software. | Regulation 17 Review 2014 | 2016-06-01 | Manager Finance & Administration | To be addressed during the development of an ICT Plan which is scheduled to be completed prior to 30/6/18. Budget item for 2017/18. | Not Commenced | N
2.5 |  | Develop a formal Information & Communication Technology framework to ensure procedures and practices are documented. | Include a budget allocation in the draft 2015/16 Budget to outsource the development on a formal ICT framework. | Regulation 17 Review 2014 | 2015-06-01 | Manager Finance & Administration | The 2017/18 budget provides an allocation to develop an ICT Strategic Framework. It is intended to address the issue of security within this document. | Not Commenced | N
2.6 |  | Review the current Email Policy on a regular basis and communicate any changes to all staff. | Communicate the Email Policy to all staff annually. | Regulation 17 Review 2014 | 2017-04-01 | HR Manager | Updated October 2017. LMS (Learning Management System) is being rolled out Email policy is currently being digitised and is planned to be rolled out to all staff December 2017 | Not Commenced | N
2.7 |  | Develop and adopt policies and procedures in respect to remote access granted to staff and communicate to staff. | Develop and present to Council for adoption a remote access policy. Include a list of staff with granted access. | Regulation 17 Review 2014 | 2016-06-01 | Manager Finance & Administration | Items to be addressed as a part of the ICT Framework document. Budget item 2017/18. | Not Commenced | N
2.7.1 |  | Include a list of users who have been granted remote access and review/update periodically. | Develop a remote access procedure. | Regulation 17 Review 2014 | 2016-06-01 | Manager Finance & Administration | Items to be addressed as a part of the ICT Framework document. Budget item 2017/18. | Not Commenced | N
2.7.2 |  |  | Communicate the adopted policy and procedure to staff with granted access. | Regulation 17 Review 2014 | 2016-06-01 | Manager Finance & Administration | Items to be addressed as a part of the ICT Framework document. Budget item 2017/18. | Not Commenced | N
2.8 |  | Develop an agreement detailing the terms and conditions of services to be provided by Sesco Security. The agreement should be signed by both parties and should as a minimum include the period of service, a confidentiality and early exit clause. | Consider the development of a formal agreement with Telstra (previous provider was Sesco). | Regulation 17 Review 2014 | 2016-12-01 | Executive Management Team |  | Not Commenced | N
2.9 |  | Develop and maintain a register of physical assets which have been allocated to staff members with periodic review conducted to ensure it’s up to date. The register may include such details as the asset number, details of the asset, the date the asset was provided to the staff member, the staff member’s acknowledgement of receipt and the date the asset was returned to the Shire. | Develop a register of physical assets allocated to staff. | Regulation 17 Review 2014 | Ongoing | Human Resources | Complete - The Physical Assets held by an employee are recorded on the employee’s personal file to ensure they can be retrieved when the employee leaves the organisation. | Completed | C
2.1 |  | Ensure employees take regular leave through ongoing management of leave scheduling and leave liabilities. | Review leave accruals at Executive Management Team Meetings. | Regulation 17 Review 2014 | Quarterly | Executive Management Team | Ongoing - Last quarterly report delivered to CEO on leave liability on 3-10-17. | In Progress | i
2.11 |  | Ensure purchase orders are completed for all purchases with exception of utilities and regular payments, whereby they are completed and authorised in accordance with policy prior to incurring expenses. | Communicate requirement for purchase orders to all staff. | Regulation 17 Review 2014 | January annually | Creditors Officer + Project Officer | Ongoing - This item is the subject of the Local Government Financial Management Regulations 1996 and CEO’s Accounting Directive #2.1. This is communicated regularly to staff and to new staff upon commencement. | In Progress | i
2.12 |  | A Contract Management framework is recommended to be designed and documented to ensure project contracts are uniformly managed appropriately and in accordance with stated framework. | To investigate developing an internal framework consisting of procedures and policies. | Regulation 17 Review 2017 | 2018-06-01 | Manager Works and Services & Occupational Health Safety | In Progress - This has been included in the OSH Coordinators KPI’s and OSH Implementation Plan (Item 18) and is due for completion in Q3 2017/18 | In Progress | i
2.12.1 |  | To include the mandatory requirement of Contractors completing some level of induction (the level of induction completed should be determined based on the risks associated with the service or product provided). |  | Regulation 17 Review 2017 |  | Manager Works and Services & Occupational Health Safety |  | In Progress | i
2.12.2 |  | A compliance checklist to be utilised to ensure compliance is met on all project contracts. |  | Regulation 17 Review 2017 |  | Manager Works and Services & Occupational Health Safety |  | In Progress | i
2.13 |  | Management shall re-communicate the requirements of the Purchasing and Tender Policy with those who have the ability to purchase goods on behalf of the Shire. | The relevant Purchasing and Tendering Policy and associated accounting directions shall be revisited and communicated to the relevant staff. | Regulation 17 Review 2017 | Ongoing | Governance Officer | Ongoing - This item is the subject of the Local Government Financial Management Regulations 1996 and CEO’s Accounting Directive #2.1. This is communicated regularly to staff and to new staff upon commencement. | In Progress | i
2.14 |  | Management shall re-communicate the requirements of the Petty Cash Policy with those with access to petty cash. | Re-communicate the requirements of the Petty Cash Policy including the need to stamp ‘PAID’ on receipt/invoices | Regulation 17 Review 2017 | Ongoing | Manager Finance and Administration | Petty Cash claims reviewed regularly. Policy is now being adhered to. | In Progress | i
2.15 |  | The Shire’s current Credit Card Policy should be updated to reflect all considerations and requirements outlined within Local Government Operational Guideline Number 11 – Use of Corporate Credit Cards. That is to include: | The Credit Card Policy shall be amended to include and address points 1.25.1, 1.25.2, 1.25.3 | Regulation 17 Review 2017 | 2017-06-01 | Governance Officer | (No Action Required) These recommendations were implemented in Financial Operational Directive (FOD), and had been communicated to the relevant card holders. The directive, which can be sighted in the Shire’s Accounting Manual, had been issued in June 2016, before the audit query arose. | Completed | C
2.15.1 |  | What the card holder should do in the event their employment ceases, an extended period of leave is taken or they have moved to a position which does not require the use of a credit card |  | Regulation 17 Review 2017 |  | Governance Officer |  | Completed | C
5.15.2 |  | What action is to be taken in the event that a cardholder fails to comply with the policies, and |  | Regulation 17 Review 2017 |  | Governance Officer |  | Completed | C
2.15.3 |  | How purchases by facsimile, telephone or over the internet are to be dealt with. |  | Regulation 17 Review 2017 |  | Governance Officer |  | Completed | C
3. LEGISLATIVE COMPLIANCE
3.1 |  | A standing agenda item should be included within the Audit Committee meeting agenda to assess the effectiveness of compliance. | A standing item shall be incorporated into the Audit Committee Agenda. | Regulation 17 Review 2017 |  | Executive Assistant | Standing agenda item included in Audit Committee Agenda - April 2017 | Completed | C
3.2 |  | Department of Local Government guidelines recommend an internal audit function be established incorporating an internal audit program which is re-assessed annually. (Note: if the Shire of Donnybrook-Balingup consider an internal audit function not be required, we suggest the Audit Committee formally document they have considered the best practice guideline and the reasons they feel it is not necessary). | The recommendation is to be put to the Risk Management Committee for their consideration at the next Committee Meeting. (Note: The Shire currently has 3 external audits each year and a further external as per the Local Government Audit Regulations). | Regulation 17 Review 2017 | 2017-11-01 | Risk Management Committee | To be considered by the Audit Committee. Was raised with the Audit Committee at its December 2017 meeting although by this time most attendees had left and so there was no quorum | Not Commenced | N
3.3 |  | Local Government Operational Guideline Number 09 – Audit in Local Government outlines it is best practice for the Audit Committee to meet on at least a quarterly basis. | The recommendation is to be put to the Risk Management Committee for their consideration at the next Committee Meeting. | Regulation 17 Review 2017 | 2017-11-01 | Risk Management Committee | To be considered by the Audit Committee. Was raised with the Audit Committee at its December 2017 meeting although by this time most attendees had left and so there was no quorum | Not Commenced | N